## IT
| Title | Phụ trách | Site | Status | Piority | Person/Day |  |  |  | Start Date | End Date ( Estimate) | % Actual | End Date (Actual) | Notes
[6 empty] | Read Document | Code | Test (Tòng) | Total |  |  | %
1 | T6_Login_PT | Vy | https://talenttech6.vn/login | Done | High | 0 | 0.5 | 0 | 0.5 | 2020-10-07 | 2020-10-07 | 100
2 | T6_Login_Test | Vy | https://talenttech6.vn/login | In Process | Low | 0 | 0.5 | 0 | 0.5 | 2020-10-08 | 2020-10-08 | 100 | 2020-10-08
3 | LD_Home_Cd | Lưu |  | Done | Low | 0 | 1.5 | 0 | 1.5 | 2020-10-09 | 2020-10-13 | 100 | 2020-10-14 | - Chưa có design trên mobile / tablet version - Nhờ Thanh vs Duy estimate ngày nhiêu có bản final "Home"
4 | LD_AboutUs_Cd | Lưu |  | Done | Low | 0 | 1.5 | 0 | 1.5 | 2020-10-14 | 2020-10-14 | 100 | 15/10/2020
5 | T6_User Test (Mobile) | Vy | https://talenttech6.vn | Done | Low | 0 | 1 | 0 | 1 | 2020-10-09 | 2020-10-12 | 100
6 | LD_Home_Test | Vy | sukien.talenttech6.com | In Process | Low |  |  |  | 1 | 2020-10-15 | 2020-10-16 | 75 |  | Mobile, Web (DONE), Tablet (Not Yet)
7 | LD_Home_Bug | Lưu | sukien.talenttech6.com | New | Low |  |  |  | 1 | 2020-10-16 | 2020-10-16 | 15 |  | Fix Kadai
8 | LD_AboutUs_Test | Vy | sukien.talenttech6.com | New | Low |  |  |  | 1 | 2020-10-16 | 2020-10-16 |  |  | Mobile, Web, Tablet
2020-10-16
2020-10-16
2020-10-16
2020-10-16
2020-10-16
2020-10-16
2020-10-16
2020-10-16
2020-10-16
2020-10-16
Note on H2: ADMIN: Unit is Date
Note on M3: ADMIN: % Actual Percent Of This Task. Input 100% if you finished

## IT_TalentTech
Title | Phụ trách | Site | Status | Piority | Person/Day |  |  |  | Start Date | End Date ( Estimate) | % Actual | End Date (Actual) | Notes
[5 empty] | Read Document | Code | Test (Tòng) | Total |  |  | %
Update postion of " Login Google/ FB " to the bottom 32px | Lưu |  | New | Low
Change Backgound Login ( Nhờ Duy gửi ) | Lưu
Layout Report Fix đúng vị trí
Note on G2: ADMIN: Unit is Date
Note on L3: ADMIN: % Actual Percent Of This Task. Input 100% if you finished

## Sheet1
x

## Master (hidden)
TestDocs | Piority | User
New | High | Vy
In Process | Medium | Tòng
Done | Low | Lưu